## sheet
Name of work : Construction of Foundations, Substructure & Superstructure along With River Training/Protection Work, Earthwork & allied works for 8 Major Bridges in Between Chainage Km 20+000 To Km 63+00, in connection with Bhanupali-Bilaspur-Beri New Railway Line in District Rupnagar of Punjab And District Bilaspur of Himachal Pradesh State, India
NAME OF CLIENT:- |  | RAIL VIKAS NIGAM LIMITED
NAME OF CONTRACT AGENCY:- |  | M/s Subhash infraengineers Pvt. LTD JV with Akelic Group LLC | [10 empty] | 2.671 FOR P2 3RD LIFT
PROJECT VALUE:- |  | 3682189438.7151 | [10 empty] | 55 CUM
PROJECT START DATE:- |  | 2023-05-06
PROJECT COMPLETION DATE:- |  | 2025-11-05
Weather :- |  | Sunny | [10 empty] | Partially Cloudy
DPR Date:- |  | 2025-04-04
Item No. | Item Description | Unit | Program for Today | Achieved Today | Achieved this Month | % Achieved this Month | Cumulative Achieved up to date | % Cumulative Achieved up to date | Tomorrow Program | Program for the month | Remark
1002a | Soil excluding rock. | Cum | 0 | 0 | 0 | 0% | 4358.95 | 1.451% | 0 | 1 |  |  | Ch. 45+450 to 45+400
NS-3 | Supplying and placing of mechanical woven double twisted hexagonal shaped wire mesh Gabion boxes of required sizes mesh type 10cmx12cm, Zn and PVC coated mesh wire dia 2.7/3.7mm (ID/OD), edges of meshes mechanically edged/selvedged with heavy coating of galvanisation as per EN-10223-3/ASTM A 975 with portions at every 1 Mtr interval and properly packed with approx 150 mm boulders including transportation and placing at indicated places as per direction of Engineer -in-charge including contractor tools, plants, labours royalty charges etc. complete in all respect and stitching with lacing wire of dia 2.2/3.2mm (ID/OD) @ 5% by weight of Gabion boxes carrying the material by head lead from nearest approach with all safety precautions and all leads and lifts. | Cum | 0 | 0 | 0 | #DIV/0! | 2898.92 | 19.99% | 0 | 0 |  |  | Br. 17 P4
2001a | Soil excluding rock. | Cum | 0 | 0 | 0 | #DIV/0! | 16659.888 | 99.65% | 0 | 0 |  |  | Br. 17 P4
2024a | Initial vertical load test. | Each | 0 | 0 | 0 | #DIV/0! | 3 | 25% | 0 | 0
2042e | Providing & laying non pressure NP-4 Class RCC pipe with collars, jointing with 1:2 Cement and ordinary sand mortar including testing of joints but excluding earth work with all labour and material as a completem job. Cement for mortar will be paid separately. | Meter | 0 | 0 | 0 | #DIV/0! | 325 | 108.3% | 0
2001a | Soil excluding rock. | Cum | 0 | 0 | 0 | 0% | 16659.888 | 99.65% | 0 | 650
NS 2004 | Providing and laying design mix control concrete M20/M25 in piers, retaining walls, wing walls, return walls, bottom/top plug of wells and protection work etc. using well graded stone aggregate of 40 MM/20 MM nominal size. (Rate is inclusive of cement.) | CUM | 0 | 0 | 44.379 | 42.58% | 617.7086 | 15.44% | 0 | 104.22 | Br. 07,P5 | 780
NS 2005d | Providing and laying Design mix control concrete M25 to M45 | CUM | 55.615 | 58.5 | 58.5 | 2.854% | 5813.076 | 18.57% | 0 | 2049.5199 | Br. 06,P2/5TH Lift, Br. 18/A1 Pile Head |  | 18 |  | 25.974
NS-2022 | Driving Bored cast in situ Reinforced Cement Concrete piles | Meter | 25 | 21 | 71 | 8.606% | 7896.5 | 45.54% | 25 | 825 | Br. 07 P6/20 | 33 | Br. 17, A2/5 |  | 3.1788
NS-2022 | installing Bored cast in situ Reinforced Cement Concrete piles | Meter | 25 | 0 | 25 | 3.03% | 7850.5 | 45.27% | 25 | 825 |  | ` | Br. 17, A2/5 |  | 22.7952 |  | 46 | 321.2
2025 | Non destructive integrity testing of cast -in- situ piles of 1500mm dia as per specifications and submitting reports in the approval format. | Each | 0 | 0 | 0 | 0% | 87 | 145% | 0 | 30
2026 | Conducting Dynamic load testing on selected piles of routine pile load test, all as per specifications. | Each | 0 | 0 | 0 | 0% | 21 | 38.18% | 0 | 2
NS-1 | Conducting Pile integrity test with cross hole ultra sonic monitoring CHUM of 1500 MM dia pile (Sonic Logging) by approved specialized agencies including the cost of providing and installation of two numbers 40mm dia oriplast C 1120 confine to AFPMB/1785 access pites for the entire length of pile to be rested as per specification, mobilization of test apparatus and submission of test results in duplicate clearly indicating the nature and extend of defect in the shaft, if and, in and approved format | Each | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 10
2059 a | Plate Girder/Semi Through Girder/Composite Girder | MT | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 1190.552
NS-1 | Supply and installing Casing pipe of MS sheet for bored piles as directed by the engineer. Note: The collar provided for strengthening of casing pipe shall also be measured under the same item for payment purposes, in addition to the casing pipe. | Meter | 2 | 3.5 | 15 | 22.73% | 1065.585 | 16.33% | 2 | 66 | Br. 07 P6/20 |  | Br. 17, A2/5 |  |  |  | 46
NNS-6 | Shifting modification of 11 KV HT Line from chainage (45.10 to 45.1000 approximately… | JOB |  | 0 | 0 |  | 1 | 100%
2076 | TMT Fe-500/Fe-500D* reinforcement steel conforming to IS:1786-1985 including decoiling, straightening, cutting, bending, placing in position, binding with 1MM dia GI binding wire. Note : 1. Reinforcement, shall be measured in length for different diameters used in the works and then paid as per standard weights as per IS 1732. Wastages, overlaps, coupling, welded joints, space bars, chairs and binding wire shall not be measured and cost of these items shall be deemed to be included in the rates. 2. * For seismic zone III, IV & V, only TMT Fe-500D steel shall be used. 3. Payment will be made on completion of scope of the item and the same is not linked to concreting. | MT | 6.6 | 6.6 | 38.172 | 7.949% | 3232.592 | 26.28% | 6.66 | 480.208 | Br. 18,P1/1 |  | Br. 17, A2/5 |  |  | 1458000
2076 | Supplying TMT Fe-500/Fe-500D* reinforcement steel | MT | 0 | 0 | 0 | 0% | 4257.711 | 34.61% | 0 | 465
9003b | BOLERO, SCORPIO, ERTIGA, MARAZZO or similar | Vehicle Month | 0 | 0 | 0 | 0% | 65.209 | 65.21% | 0 | 3 |  | 17.64
Nos. of Piles |  |  | 1 | 0 | 1 |  | 314.02 |  | 1 | 33
[13 empty] | 46 |  | 96
Target Amount for Month of March'2025 |  | 108096438.2978 | [9 empty] | 315.86
Target Amount for Today |  | 1543028.2812
Amount Achieved Today |  | 1369192.5915 | [10 empty] | 1.0714
Amount Achieved this Month |  | 4008740.7672 | [12 empty] | 96
Amount Achieved Up to Date |  | 652819060.1378
Work Done % age Up to Date |  | 17.33% | [10 empty] | 234
[13 empty] | 233 |  | 0.037085
Labour Reports
Sr. No. | Work Description | Nos.
1 | Bar Binders & Helpers | 43 | [11 empty] | 35
2 | Concrete Work | 6
3 | Liner Work | 2 | [10 empty] | 32
4 | Other Work | 21
Note:- 1) Br. No. 07 work hampered due approach road closed by Villagers.
[13 empty] | 109 |  | 75 | 74750 | 82225
[13 empty] | 20 | 75 | 22 | 98
|  | BRIDGE -6 | [7 empty] | BRIDGE -7 |  |  |  |  | 99
| Abutment | Work | Total No. of Piles | No. of Piles (Upto date ) |  |  | Abutment |  | Work | Total No. of Piles | No. of Piles (Upto date )
| Br 6 (A1) | Piling Work | 12 | 12 |  |  | Br 7 (A1) |  | Piling Work | 20 | 12 | 8
| Br 6 (A2) | Piling Work | 12 | 12 |  |  | Br 7 (A2) |  | Piling Work | 20 | 12 | 8 | 371.79
| Br 6 (P1) | Piling Work | 9 | 9 |  |  | Br 7 (P1) |  | Piling Work | 20 |  | 20 |  | 96
| Br 6 (P2) | Piling Work | 12 | 12 |  |  | Br 7 (P2) |  | Piling Work | 25 | 12 | 13
| Br 6 (P3) | Piling Work | 12 | 12 |  |  | Br 7 (P3) |  | Piling Work | 20 | 20 | 0
| Br 6 (P4) | Piling Work | 12 | 12 |  |  | Br 7 (P4) |  | Piling Work | 20 | 20 | 0
| Br 6 (P5) | Piling Work | 9 | 9 |  |  | Br 7 (P5) |  | Piling Work | 20 | 20 | 0
|  |  | 78 | 78 |  |  | Br 7 (P6) |  | Piling Work | 20 | 19 | 1
[10 empty] | 165 | 115 | [5 empty] | 90
|  | Planing VS Achived | [7 empty] | BRIDGE -17 |  |  |  |  | 99 |  | 99
| Abutment | Work | Work Plan | Achived this Month |  |  | Abutment |  | Work | Total No. of Piles | No. of Piles (Upto date ) |  | 297
| Br 7 ( P6) | Pile Nos. | 1 |  |  |  | Br 17 Test Pile |  | Piling Work | 1 | 1 | 0
| Br 7 ( A2) | Pile Nos. | 8 |  |  |  | Br 17 (A2) |  | Piling Work | 15 | 15 | 0
| Br 18 ( A2) | Pile Nos. | 12 |  |  |  | Br 17 (P12) |  | Piling Work | 9 | 9 | 0
| Br 18 ( P1) | Pile Nos. | 12 | 1 |  |  | Br 17 (P11) |  | Piling Work | 9 | 9 | 1
| Br 17 ( P1) | Pier Length | 3.67 |  | 9 |  | Br 17 (P10) |  | Piling Work | 9 | 9 | 0
| Br 17 ( P10) | Pier Length | 3.67 |  |  |  | Br 17 (P9) |  | Piling Work | 9 | 8
| Br 17 ( P5) | Pier Length | 1.697 |  |  |  | Br 17 (P8) |  | Piling Work | 9 | 9
| Br 06 ( P3) | Pier Length | 5.637 |  |  |  | Br 17 (P7) |  | Piling Work | 9 | 9
| Br 06 ( P4) | Pier Length | 12 |  |  |  | Br 17 (P6) |  | Piling Work | 9 |  | 0
[7 empty] | Br 17 (P5) |  | Piling Work | 9 | 9 | 9
[7 empty] | Br 17 (P4) |  | Piling Work | 9 | 9 | 0
[7 empty] | Br 17 (P3) |  | Piling Work | 9 |  | 0
[7 empty] | Br 17 (P2) |  | Piling Work | 9 | 6 | 9
[7 empty] | Br 17 (P1) |  | Piling Work | 9 | 9 | 3
|  |  | BRIDGE -18 |  |  |  | Br 17 (A1) |  | Piling Work | 12 |  | 0
| Work | Total No. of Piles | No. of Piles (Upto date ) | [6 empty] | 136 | 102 | 12
Br 18Test Pile | Piling Work | 1 | 1 | [8 empty] | 34
Br 18 (A1) | Piling Work | 15 | 15
Br 18 (P1) | Piling Work | 12 | 1
Br 18 (A2) | Piling Work | 15
297